## Cover
QUALITEH ACADEMY
8D Problem-Solving Report
Eight Disciplines
Structured per the Ford Global 8D / AIAG problem-solving methodology
What this template gives you:
A complete, interactive 8D form (D0–D8) pre-filled with a worked example — so your first report is guided, not guesswork.
Built-in root-cause tools: 5-Why ladders (occurrence + escape) and Ishikawa / Fishbone 6M.
A live action dashboard with discipline counts, owner breakdown, completion % and overdue alerts — charts update automatically.
Data-validation dropdowns, date formatting and sheet protection ready to use. Designed for quality engineers in Tier-1/2 automotive.
Run 8D/A3 with AEI — qualiteh.com
Hands-on quality workshops — qualiteh.com/academy
v1.0 · 2026 · © Qualiteh Academy
qualiteh.com · rankovic@qualiteh.com

## How to use
How to use this template
8D Problem-Solving Report — structured per the Ford Global 8D / AIAG methodology
The Eight Disciplines (D0–D8)
| D0 Plan / Prepare | Confirm the symptom warrants an 8D. Define the Emergency Response Action (ERA) to protect the customer immediately.
| D1 Team | Form a cross-functional team with the knowledge, authority and time to solve the problem.
| D2 Describe the Problem | Quantify the problem using 5W2H (What / Where / When / Who / Why / How / How many) and an Is / Is-Not table.
| D3 Interim Containment (ICA) | Implement and verify containment actions to protect the customer while the permanent fix is developed.
| D4 Root Cause Analysis | Identify and verify the occurrence root cause, the escape / detection root cause, and the systemic root cause.
| D5 Permanent Corrective Actions | Select and verify PCAs that address all three root causes (D4). Confirm before implementation.
| D6 Implement & Validate PCA | Implement the PCAs, confirm effectiveness with data (e.g. Cpk ≥ 1.67), and remove the ICA once validated.
| D7 Prevent Recurrence | Update PFMEA, Control Plan, Work Instructions, Standards, and Lessons Learned. Read across to similar products/processes.
| D8 Recognise the Team | Celebrate team success. Capture lessons learned. Close the 8D with Champion sign-off.
Input cells vs auto / formula cells
| Input cells (white, unlocked) | All white cells in the '8D Report', 'Root-cause tools', and 'Action tracker + Dashboard' sheets are for your input. They are unlocked so you can type directly. Dropdowns guide Status, Discipline, and document-type fields.
| Auto / formula cells (locked) | Dashboard KPI cells, chart helper tables, and the Completion % cell use live formulas and are locked. The dashboard updates the moment you change any tracker row.
Working tips
| Dropdowns | Status uses Open / In-progress / Done. Discipline uses D3 / D5 / D6 / D7. Verification fields use Yes / No / Pending. 'Document to update' in D7 uses FMEA / Control Plan / Work Instruction / Standard / Lessons Learned.
| Date format | Enter dates as yyyy-mm-dd (e.g. 2026-09-30). Date columns are pre-formatted.
| Sheet protection | Sheets are protected without a password. To edit the structure (add rows, change formulas), use Review ▸ Unprotect Sheet.
| PFMEA link | In D7, update your PFMEA, Control Plan and Work Instructions — see Qualiteh's Process FMEA template (process-fmea-template.xlsx).
| AEI acceleration | Qualiteh Sync (8D/A3) runs guided problem-solving with AEI — auto-drafts root causes, corrective actions and read-across. qualiteh.com
Qualiteh Academy · qualiteh.com · rankovic@qualiteh.com · Structured per the Ford Global 8D / AIAG problem-solving methodology · v1.0

## 8D Report
8D Problem-Solving Report
Eight Disciplines — structured per the Ford Global 8D / AIAG problem-solving methodology
Report Header
| Report No. | 8D-2026-001 | Part / Process | Connector type A (12-pin, grey) — OP-70 crimp
| Customer (generic) | Major OEM — Western Europe | Defect / Symptom | Intermittent electrical open — continuity failure at field return
| Date opened | 2026-01-20 | Target close date | 2026-06-30
| Current status | In progress — D7 prevention & 60-day monitoring open
D0 Plan / Prepare — Symptom Statement & Emergency Response
| Symptom statement | Intermittent loss of electrical continuity in connector type A (12-pin, grey) returned from field. Customer sorting line flagged 0.8% in-plant rate. ERA: 100% containment sort at customer ship-dock + 100% sort at Qualiteh dock.
| Emergency Response Action (ERA) | 100% electrical continuity test at customer sorting line; 100% test at Qualiteh outgoing dock. Suspect stock quarantined (Lot 2026-01-A, Qty 3 400 pcs).
| ERA verified? | Yes
D1 Team — Champion, Leader & Members
| Champion | Plant Quality Manager | Team Leader | Quality Engineer (Weber, J.)
| Team member | Process Engineer (Kern, T.) | Function | Process Engineering
| Team member | Maintenance Technician (Fuchs, R.) | Function | Maintenance
| Team member | Production Supervisor (Bauer, S.) | Function | Production
| Team member | Supplier Quality Engineer (Woll, P.) | Function | Supplier Quality
D2 Describe the Problem — 5W2H
| Dimension | Description
| What | Loss of electrical continuity on connector type A (12-pin). Open-circuit detected at EOL tester.
| Where | Line 2, Station OP-70 (EOL test), Shift C (night). Connector type A only.
| When | First detected 2026-01-15. Elevated rate over 3 consecutive nights. Not observed on day shift.
| Who | Assembly operators on Shift C. No specific individual pattern; machine-linked.
| Why | Crimp applicator wear causing crimp height to drift above upper tolerance.
| How | Crimp height drifts → reduced contact area → intermittent open circuit under vibration.
| How many | 0.8% of shipped connectors (27 of 3 400 pcs, Lot 2026-07-A). 0% on other connector types.
Is / Is-Not Analysis
| Dimension | Is | Is-Not | Distinction / Change
| What / Object | Connector type A (12-pin, grey) | Connector type B, C or any other | Only type A uses the affected crimp applicator tool #7.
| Where | Line 2, OP-70, Applicator #7 | Line 1 (Applicator #3), Line 3 (Applicator #9) | Tool #7 last PMed 2025-12-01 — 400k cycles ago; PM interval is 350k.
| When | Night shift (Shift C) 2026-01-12 → 2026-01-15 | Day/afternoon shifts; prior to 2026-01-12 | Crimp-height Cpk records show capability decline starting night of 2026-01-12.
| Extent | 0.8% affected (27 / 3 400 pcs) | Remaining 99.2% test OK | Failures cluster in last 3 hours of Shift C (applicator most worn).
D3 Interim Containment Actions (ICA)
| Action | Owner | Date | % effective
| 100% electrical continuity sort of all Lot 2026-01-A stock at customer dock — segregate NOK units. | Quality Engineer (Weber, J.) | 2026-01-21 | 100
| 100% crimp-height check on Tool #7 output (go/no-go gauge per dwg) at OP-70 — hold all suspect connectors. | Process Engineer (Kern, T.) | 2026-01-21 | 100
| Replace crimp applicator Tool #7 with standby unit pending root-cause confirmation. | Maintenance (Fuchs, R.) | 2026-01-22 | 100
D4 Root Cause Analysis
| Occurrence root cause (why did it happen?) | Crimp applicator Tool #7 worn beyond PM interval (actual cycles: 400k; PM interval: 350k). Worn tooling shifts crimp height above upper specification, reducing contact area.
| Escape / Detection root cause (why wasn't it detected?) | End-of-line continuity test at OP-70 relies on static load; intermittent opens under vibration not detected. Test spec did not require vibration-induced continuity check for connector type A.
| Systemic root cause (why did the system allow it?) | No Cpk monitoring on crimp height for connector type A. PM interval tracking was manual (spreadsheet) with no automated alert at 350k cycles. No escalation trigger when Cpk trends below 1.33.
→ Use the 'Root-cause tools' sheet for guided 5-Why ladders (occurrence + escape) and Ishikawa / Fishbone 6M.
D5 Permanent Corrective Actions (PCA) — Chosen
| PCA description | Owner | Verified before impl.? | Target date
| Replace crimp applicator Tool #7 and reset PM interval to 300k cycles. Update PM work instruction. | Maintenance (Fuchs, R.) | Yes | 2026-02-15
| Implement SPC on crimp height at OP-70 for connector type A (Xbar-R chart, 5 pcs every 2 hrs). Alert at Cpk < 1.33. | Process Engineer (Kern, T.) | Yes | 2026-03-01
| Add poka-yoke: digital crimp-height measurement at OP-70 with automatic NOK lock-out (spec ±0.05 mm). | Process Engineer (Kern, T.) | Yes | 2026-03-31
D6 Implement & Validate PCA
| Action implemented | Owner | Effectiveness confirmed? | Date
| New Tool #7 installed. PM interval updated in CMMS to 300k cycles with automated alert. | Maintenance (Fuchs, R.) | Yes | 2026-02-18
| SPC chart live on Line 2 OP-70. Baseline Cpk = 1.74 on 300 consecutive connectors. | Process Engineer (Kern, T.) | Yes | 2026-03-05
| Digital crimp-height gauge with NOK lockout installed. 500-pc capability study: Cpk = 1.82. | Process Engineer (Kern, T.) | Yes | 2026-04-12
→ Remove ICA (D3) once PCA effectiveness is confirmed. Update PFMEA and Control Plan (D7).
D7 Prevent Recurrence — Systemic Actions
| Systemic preventive action | Owner | Document to update | Date
| Update PFMEA: revise detection rating for crimp-height drift to reflect new SPC + poka-yoke controls. | Quality Engineer (Weber, J.) | FMEA | 2026-04-20
| Add crimp height (Xbar-R at 300k cycles) to Control Plan for connector type A Line 2. | Quality Engineer (Weber, J.) | Control Plan | 2026-04-20
| Update Work Instruction WI-OP70-004: document crimp-height gauge procedure and PM trigger. | Process Engineer (Kern, T.) | Work Instruction | 2026-05-05
| Read-across: audit crimp-height PM status on Lines 1 and 3 (Applicators #3, #9). Update PM schedule. | Supplier Quality Eng. (Woll, P.) | Lessons Learned | 2026-05-20
D8 Recognise the Team & Close the 8D
| Closure statement | Closure pending. Root cause (crimp applicator wear) confirmed and eliminated; containment verified 100% effective (0 field escapes post-ERA); PCA effectiveness confirmed (Cpk ≥ 1.67 on 500-pc study); PFMEA and Control Plan updated. Remaining before sign-off: complete D7 prevention (WI update + read-across to Lines 1 & 3) and the 60-day zero-recurrence monitoring window.
| Team recognition | The 8D team is recognised for rapid response, thorough root-cause investigation, and disciplined verification. Special acknowledgement to Process Engineering for the digital crimp-height solution delivered ahead of schedule. Final recognition on closure.
| Champion sign-off | Pending — sign-off on completion of D7 prevention + 60-day monitoring | Closure date | Pending (target 2026-06-30)
Qualiteh Academy · qualiteh.com · rankovic@qualiteh.com · Structured per the Ford Global 8D / AIAG problem-solving methodology · v1.0

## Root-cause tools
Root-cause tools
5-Why ladders (Occurrence & Escape) and Ishikawa / Fishbone 6M
5-Why — Occurrence Root Cause
Occurrence 5-Why — Problem statement (from D4):
Crimp height on connector type A drifts above upper specification on Line 2 OP-70 during night shift (Shift C).
| Why 1 | End-of-shift crimp quality monitoring showed Cpk trending toward 1.33 — but no alert fired.
| Why 2 | Cpk monitoring was tracking, but no automated escalation at the control limit.
| Why 3 | The control plan did not specify a lower Cpk alert threshold for Tool #7.
| Why 4 | Tool #7 had exceeded its PM interval (400k vs 350k cycles); worn tooling shifted the crimp height.
| Why 5 | PM interval tracking was manual (spreadsheet) with no automated alert at 350k cycles.
Root cause identified: Crimp applicator Tool #7 worn beyond PM interval due to lack of automated cycle-count alert. Worn tooling shifted crimp height above upper specification.
5-Why — Escape / Detection Root Cause
Escape / Detection 5-Why — Problem statement (from D4):
Connectors with intermittent open circuits passed EOL test and were shipped to customer.
| Why 1 | EOL continuity tester did not detect the intermittent open in static conditions.
| Why 2 | Test specification required static continuity only; no vibration-induced load was applied.
| Why 3 | The connector type A test spec had not been updated when the vibration profile was revised in 2025.
| Why 4 | Spec revision process did not include a mandatory re-evaluation of the EOL test method.
| Why 5 | No trigger existed to re-validate EOL test coverage when product vibration requirements changed.
Root cause identified: EOL continuity test spec not updated when vibration profile changed; test did not simulate the in-service load under which the intermittent open occurs.
Ishikawa / Fishbone 6M — Central Problem / Effect
Problem / Effect: Intermittent loss of electrical continuity in connector type A — 0.8% field-return rate.
| Man |  | Machine
| → | Night shift operator not notified of Cpk trend at Tool #7. | → | Crimp applicator Tool #7 worn — 400k cycles (PM interval 350k).
| → | No clear escalation checklist for sub-spec Cpk. | → | No automated cycle counter or PM alert on applicator.
| → | Training on crimp-height SPC not yet completed. | → | Standby applicator not pre-qualified for this connector.
| Method |  | Material
| → | PM interval tracking via manual spreadsheet — no alert system. | → | Connector type A contact geometry sensitive to crimp height tolerance.
| → | EOL test spec not updated after vibration profile revision (2025). | → | No material-specific control limit documented for this connector.
| → | No periodic re-validation of test method vs. product requirement. | →
| Measurement |  | Mother-Nature / Environment
| → | EOL tester: static continuity only — misses vibration-induced opens. | → | Night shift temperature variation may increase applicator wear rate.
| → | Crimp-height Cpk data existed but no SPC alert threshold set. | → | Vibration from adjacent press influences loose contact detection threshold.
| → | MSA not performed on crimp-height measurement system. | →
Qualiteh Academy · qualiteh.com · rankovic@qualiteh.com · Structured per the Ford Global 8D / AIAG problem-solving methodology · v1.0

## Action tracker + Dashboard
Action tracker + Dashboard
Single source of truth for all 8D actions — dashboard updates automatically
# | Action description | Discipline | Owner | Due date | Status | Completion date
1 | 100% electrical continuity sort — customer dock. Quarantine NOK stock. | D3 | Quality Engineer (Weber, J.) | 2026-01-21 | Done | 2026-01-21
2 | 100% crimp-height check at OP-70 (go/no-go gauge) — hold suspect connectors. | D3 | Process Engineer (Kern, T.) | 2026-01-21 | Done | 2026-01-21
3 | Replace crimp applicator Tool #7 with standby unit. | D3 | Maintenance (Fuchs, R.) | 2026-01-22 | Done | 2026-01-22
4 | Replace Tool #7 (permanent). Reset PM interval to 300k. Update CMMS. | D5 | Maintenance (Fuchs, R.) | 2026-02-15 | Done | 2026-02-18
5 | Implement SPC on crimp height at OP-70 — Xbar-R chart, 5 pcs / 2 hrs. | D5 | Process Engineer (Kern, T.) | 2026-03-01 | Done | 2026-03-05
6 | Digital crimp-height gauge + NOK lockout installed at OP-70. | D5 | Process Engineer (Kern, T.) | 2026-03-31 | Done | 2026-04-08
7 | Confirm SPC effectiveness: baseline Cpk ≥ 1.33 on 300 connectors. | D6 | Quality Engineer (Weber, J.) | 2026-03-10 | Done | 2026-03-09
8 | Confirm poka-yoke effectiveness: Cpk ≥ 1.67 on 500-pc capability study. | D6 | Process Engineer (Kern, T.) | 2026-04-15 | Done | 2026-04-12
9 | Update PFMEA detection rating for connector type A crimp-height drift. | D7 | Quality Engineer (Weber, J.) | 2026-04-20 | Done | 2026-04-22
10 | Update Control Plan: add crimp-height SPC to Line 2 OP-70. | D7 | Quality Engineer (Weber, J.) | 2026-04-20 | Done | 2026-04-22
11 | Update WI-OP70-004: crimp-height gauge procedure + PM trigger. | D7 | Process Engineer (Kern, T.) | 2026-05-05 | In-progress
12 | Read-across audit Lines 1 & 3 (Applicators #3, #9). Update PM schedule. | D7 | Supplier Quality Eng. (Woll, P.) | 2026-05-20 | In-progress
13 | 60-day zero-recurrence monitoring window — check field returns log. | D6 | Quality Engineer (Weber, J.) | 2026-06-30 | Open
Live Dashboard — updates automatically as tracker rows change
TOTAL ACTIONS |  |  |  | DONE
IN-PROGRESS |  |  |  | OPEN
COMPLETION % |  |  |  | OVERDUE (NOT DONE)
Chart data (auto)
Discipline | Count
D3
D5
D6
D7
Status | Count
Open
In-progress
Done
Owner | Total actions
Quality Engineer (Weber, J.)
Process Engineer (Kern, T.)
Maintenance (Fuchs, R.)
Supplier Quality Eng. (Woll, P.)
Closure timing | Count
On-time (Done ≤ Due)
Late (Done > Due)
Qualiteh Academy · qualiteh.com · rankovic@qualiteh.com · Structured per the Ford Global 8D / AIAG problem-solving methodology · v1.0

## Qualiteh OS
Qualiteh OS — Run 8D/A3 at the speed of AEI
Augmented Engineering Intelligence for quality teams
You just ran an 8D by hand.
Qualiteh Sync (8D/A3) runs Eight Disciplines with AEI — guided disciplines, auto-drafted root-cause analysis and corrective actions, a complete audit trail, and read-across across the plant — so your team closes loops faster and prevents recurrence systemically. No more blank forms. No missed disciplines. No lost closure evidence.
The Qualiteh OS suite
| Product | What it gives your team
| Qualiteh Sync (8D/A3) | Guided problem-solving with AEI — structured disciplines, auto-drafted root causes and corrective actions, full audit trail.
| Qualiteh Audit | Offline-first VDA 6.3 and layered process audits. Mobile-first, works in-plant without connectivity.
| KPI Sentinel | Plant KPIs and cost-of-poor-quality reduction. Live dashboards with AEI-powered trend alerts.
| PPAP Assistant (Lens) | Faster PPAP submissions. AEI guides your team through all 18 elements with evidence checklists.
| Tacit CRM | Quality-led customer relationships. Track commitments, action status and customer contacts in one place.
Run 8D/A3 with AEI — qualiteh.com
Hands-on quality workshops — qualiteh.com/academy
AEI — Augmented Engineering Intelligence — is Qualiteh's term for the structured, context-aware guidance layer embedded in our products. It is a working aid that supports, and does not replace, engineering judgement.
Qualiteh Academy · qualiteh.com · rankovic@qualiteh.com · Structured per the Ford Global 8D / AIAG problem-solving methodology · v1.0

## Revision history
Revision history
| Version | Date | Author | Notes
| v1.0 | 2026 | Qualiteh Academy | Initial release — 8D Problem-Solving Report (D0–D8) with 5-Why ladders, Ishikawa 6M, live action tracker + dashboard (named ranges, charts, conditional formatting). Worked example: wiring-harness connector / crimp-height drift.
Qualiteh Academy · qualiteh.com · rankovic@qualiteh.com · Structured per the Ford Global 8D / AIAG problem-solving methodology · v1.0